## a. MEAL Plan Instructions
ADO Detailed MEAL Plan Tools Instructions
1. Complete the M&E Matrix: It can be developed within the tab or within a Word document and transferred to the M&E Matrix tab.
· The M&E Matrix is a critical tool for planning and managing data collection, analysis, and use within the nexus approach , bridging humanitarian assistance, development cooperation, and peacebuilding efforts. · It can be developed within the tab or in a Word document and transferred to the M&E Matrix tab .
a. For detailed instructions on completing the content of the M&E Matrix, please refer to tab c. M&E Matrix Cheat Sheet.
b. Enter the objective statements and indicators ONLY in the M&E Matrix. They are automatically linked to the Indicator Tracking Table (ITT) and the Activity Tracking Table (ATT), ensuring alignment with the nexus framework.
2. Baseline Table:
a. Fill in the Baseline Table after or as the baseline data is collected either by a consultant or the project team.
b. Ensure baseline data reflects the starting points for indicators across humanitarian, development, and peacebuilding efforts, supporting the nexus approach.
3. Complete the Indicator Tracking Table: See tab i. for further instructions on using the ITT.
a. Fill in the Project Name and the Project Year (PY) for the ITT. The blank version of this workbook contains linked ITT and ATT tables for up to a three year project.
b. Fill in the baseline values for each indicator including the date it was collected and the unit of measurement. If the baseline values do not come from a consolidated baseline survey, note in the status column where the values are archived (the document, file, government database, etc). The baseline values are automatically populated in the Year 2 and Year 3 ITTs in the blank workbook.
4. Set indicator targets:
a. Indicator targets should be set for each indicator based upon the details outlined in the project proposal taking into consideration timelines, number of staff, and budget. Start with Life of Project (LOP) targets, then annual targets, then quarterly targets. Targets should be based on the project’s work plan/detailed implementation plan.
i. All targets and actuals should be cumulative. This means that targets and actuals recorded for each quarter reflect what has been targeted or achieved to date. If a given indicator cannot be recorded in a cumulative manner for some reason, include a note in the status column.
ii. Values for indicators should be numeric with narrative detail reserved for the Narrative Report.
iii. LOP targets will be included in each ITT on an annual basis. The LOP targets should remain the same throughout, but in each new annual ITT any cumulative data should be transferred.
iv. Impact indicators (Outcome and Goal) are often measured at the start of project (baseline) and end of project (endline) and therefore will only require LOP targets. Shade out the reporting periods that do not have targets so that reviewers are clear that no data will be gathered during that period.
b. The values in the "Target" and "Actual" columns should be entered as whole numbers, not percentages. This will help to ensure that the numerator and denominator are clearly expressed, which reduces calculation errors.
c. Formulas can be used in Excel so that percentages and other calculations are done automatically, reducing the amount of data that must be entered manually. However, formulas can be tricky and should be double-checked to ensure that the data has been calculated correctly.
5. Using the Indicator Tracking Table:
a. Actual data should be collected during the reporting period and validated for accuracy. It is not an estimate or guess. If you are confused about what an indicator means or how to enter the data, refer to your project’s M&E Matrix.
b. The ITT should be filled out on a quarterly basis, before starting work on the Project Progress Report.
c. Some indicators will require the roll-up of data from multiple communities, districts, regions, etc. The primary data from each individual source should be kept in another tab within this file, with the sum linked to the Actual column for that indicator. This will help assist in data verification.
d. Make sure to update actual beneficiary numbers in the ITT in each project reporting period, ensuring alignment with the nexus approach.
6. Complete the Activity Tracking Table: The ATT is a complimentary tool to the ITT. It allows activities to be tracked in a summary manner in a separate tab from the indicators so that the progress towards the project indicators in the ITT can be easily read. See tab k. for further instructions on using the ATT.
a. List the high level projects activities in the first column as outlined in the project proposal. Ensure activities under each Output are necessary and sufficient to achieve the Output, reflecting contributions to humanitarian, development, and peacebuilding efforts.
b. Complete the "targets" for each activity for each reporting period, year, and LOP. Targets should be developed using the project's detailed implementation plan.
c. The ATT should be filled out on a quarterly basis with activities accomplished during the reporting period.
d. For each reporting period, update the status of the activity in column W. It should be updated with "Not yet started," In progress," or "Completed." If it is completed, list the date completed.
7. Cpmplate the Project Work Plan: The project Work Plan is a detailed roadmap for implementing project activities, aligned with the nexus approach to bridge humanitarian assistance, development cooperation, and peacebuilding efforts. It ensures coherence and synergy across these pillars by linking activities to objectives and indicators in the M&E Matrix . Key steps include:
a. Timelines and Milestones: Define realistic timelines and key milestones, considering local context and dynamics.
b. Responsibility Assignment: Assign clear roles to individuals or teams, fostering collaboration across sectors.
c. Resource Allocation: Allocate resources equitably and include contingency plans for emergencies.
d. Iterative Updates: Regularly update the Work Plan to reflect progress, align with M&E tools (e.g., ITT, ATT), and adapt to changing contexts.
e. Risk Management: Identify risks and mitigation strategies, ensuring context-sensitive and conflict-sensitive implementation.
f. Gender and Inclusion: Incorporate gender-sensitive activities and disaggregate data to address inequalities.

## b. M&E Matrix Description
TOOL SUMMARY: M&E MATRIX INSTRUCTIONS
Purpose | The purpose of this tool is to guide staff in completing each column of the M&E Matrix, ensuring alignment with the nexus approach —a strategic framework that bridges humanitarian assistance, development cooperation, and peacebuilding efforts.
· The M&E Matrix is a critical tool for planning and managing data collection, analysis, and use within the nexus framework. It expands on the Logframe to identify key information requirements for each indicator and summarizes the essential M&E tasks for the project.
o It helps staff determine if proposed indicators can effectively measure results across the humanitarian-development-peace nexus.
o It ensures that indicators are feasible to collect given time, resource constraints, and the interconnected nature of nexus programming.
Information Sources | Information the project team should have before starting the M&E Matrix:
· Logframe (aligned with the nexus approach)
· Project Proposal (M&E Plan) incorporating humanitarian, development, and peacebuilding objectives
Guidance for M&E Matrix:
- CRS SMILER Guide - IFRC Project Planning Guidance Manual - Relevant nexus-specific frameworks (e.g., UNDP’s Triple Nexus Framework, OECD DAC recommendations)
Who | This tool is a reference that can be used by any staff working to complete the M&E Matrix, including humanitarian, development, and peacebuilding practitioners collaborating under the nexus approach.
When | Given that the M&E Matrix helps define the scope (cost, time) of the project’s monitoring system, it is recommended that the following columns be completed before finalizing the project proposal: '- Indicator Definition - Frequency/Schedule - Responsible Person
The remaining columns of the M&E Matrix should be filled out as information becomes available but must be finalized within the following timeframes:
· Projects 1 year or less: complete a detailed M&E plan within 60 days of the project approval
· Projects with a duration of 1-3 years: complete a detailed M&E plan within 90 days of the project approval
· Projects with a duration of 3-5 years: complete a detailed M&E plan within 120 days of project approval
Requirements | REQUIREMENTS:
· This M&E Matrix should be used for all projects adopting the nexus approach.
· The M&E Matrix is a living document and should be updated based on relevant project adjustments, particularly in response to evolving humanitarian, development, and peacebuilding needs.
o If changes are made to the M&E Matrix, report the changes, the reason, and how they affect other aspects of the M&E and project implementation plan.
o Ensure that HQ, the country office, partners, and stakeholders involved in the nexus approach have the updated version.
RECOMMENDATIONS:
· Ideally, the M&E Matrix will be finalized during a joint project planning meeting (project kick-off meeting) with participation from key partners, humanitarian actors, development practitioners, and peacebuilding experts.
SMART Criteria:
· Use SMART criteria (Specific, Measurable, Attainable, Relevant, and Timebound) for indicators to ensure they align with the nexus approach.
· Objective statements in the Logframe should NOT be written using SMART criteria but may be used effectively within project proposals to detail expected results.
· SMART criteria should be applied to indicators, not objective statements. (reference p. 37 of IFRC Project Planning Guidance Manual for further information on SMART criteria).
· Follow the instructions and examples for writing indicators found in the Logframe Cheat Sheet.
· As presented in the Logframe, each indicator may not meet all the SMART criteria, but once the M&E Matrix is fully developed the indicators should be SMART.
Tips | · Collaborative Development: The M&E Matrix should be completed collaboratively by those who will use it, including representatives from humanitarian, development, and peacebuilding teams. This allows the project team to crosscheck the Logframe and indicators before implementation, ensuring they are sensitive to field realities, capacities, and the interconnected nature of nexus programming. Team involvement reinforces understanding of data collection responsibilities and methods.
· Scale and Realism: Keep the M&E Matrix appropriate for the scale and timeframe of the project. Remember, it should be “good enough” while balancing qualitative and quantitative data to measure indicators realistically.
· Ownership and Accountability: Clearly designate a person within the project team to “own the M&E Matrix.” This includes: - Ensuring it is thoroughly completed. - Sharing it with all relevant stakeholders (humanitarian, development, and peacebuilding actors). - Incorporating and communicating any changes. - Regularly monitoring and managing outlined tasks. - Managing the Indicator Tracking Table and Activity Tracking Table.
· Alignment with Donor Requirements: The M&E Matrix is nearly identical to USAID’s Performance Monitoring Plan (PMP). These instructions can also be applied to complete donor-specific M&E tools, ensuring alignment with nexus principles.
How to Address Gender Issues | · Sex-disaggregate data of all indicators for which people are the unit of measure.
· Include qualitative and quantitative indicators to capture gender dynamics and their intersection with humanitarian, development, and peacebuilding outcomes.
· Ensure gender-sensitive indicators are included to monitor progress toward reducing inequalities and promoting inclusive development and peace.
Key Considerations for the Nexus Approach | · Humanitarian-Development-Peace Linkages: Ensure indicators reflect the interconnections between humanitarian assistance, development cooperation, and peacebuilding efforts. For example: - Humanitarian indicators might focus on immediate needs (e.g., food security, shelter). - Development indicators might track long-term resilience-building (e.g., livelihoods, education). - Peacebuilding indicators might measure social cohesion, conflict resolution, or governance improvements.
· Context Sensitivity: Tailor indicators to the local context, considering the unique challenges and opportunities at the intersection of humanitarian crises, development gaps, and peacebuilding priorities.
· Participatory Approaches: Engage affected communities, local stakeholders, and partners in defining indicators and data collection methods to ensure relevance and ownership.

## c. M&E Matrix Cheat Sheet
M&E Matrix Cheat Sheet
PERFORMANCE INDICATORS |  |  | DATA GATHERING |  |  |  | ANALYSIS, USE, REPORTING
Indicator | Indicator Definition | Unit of Measurement | Method | Means of Verification (Data Source/Tools) | Frequency & Schedule | Responsible Person | Data Analysis | Information Use/Audience | Reporting
- Indicators are taken from the logframe. When transferring them, ensure they align with the nexus approach , bridging humanitarian assistance, development cooperation, and peacebuilding efforts. - Ensure indicators are SMART (Specific, Measurable, Achievable, Relevant, and Time-bound) and reflect linkages across the nexus framework. - Revise indicators as needed to reflect field realities, donor requirements, and evolving needs in humanitarian, development, and peacebuilding contexts. Ensure updates are reflected in both the M&E Matrix and the logframe. | - Provide a detailed definition of each indicator’s key terms, including explanations of who, what, where, and how the indicator applies. - Define subjective terms (e.g., “appropriate,” “successful,” “sustainable”) clearly to ensure consistency across humanitarian, development, and peacebuilding contexts. - Specify how the indicator will be calculated (e.g., numerator/denominator for percentages). Include whether the indicator will be disaggregated by sex, age, ethnicity, or other relevant variables to address inequalities and promote inclusivity. - Interconnected Indicators: Ensure indicators reflect linkages between humanitarian, development, and peacebuilding efforts. For example: Humanitarian indicators: Immediate needs (e.g., food security, shelter). Development indicators: Long-term resilience (e.g., livelihoods, education). Peacebuilding indicators: Social cohesion, governance, conflict resolution. | - Each indicator must have a clear unit of measure (e.g., number of people, percentage, score, etc.). Ensure units are appropriate for the context and aligned with the nexus approach (e.g., resilience scores, conflict resolution rates, food security levels). - Disaggregate data by sex, age, and other relevant variables to address inequalities and promote inclusive development and peace. | - Outline the methods for data collection during baseline, monitoring, and endline phases. Examples include secondary data analysis, surveys, participatory rural appraisals (PRA), focus group discussions (FGDs), key informant interviews, and community-based monitoring. - Ensure methods align with the Means of Verification and are tailored to the humanitarian-development-peace nexus. For example, use participatory methods to engage affected communities in defining and tracking progress. | - Identify all sources of information for each indicator. If multiple sources are listed, specify how data will be aggregated into a single data point for entry into the Indicator Tracking Table (ITT). - Indicate whether data collection tools (e.g., questionnaires, checklists) already exist or need to be developed. Tools should be designed to capture qualitative and quantitative data relevant to the nexus approach. | - Specify the frequency (e.g., monthly, quarterly, annually) and schedule (day/month/year) for data collection. Align timing with seasonal variations, cultural calendars (e.g., planting/harvest periods, Ramadan), and project milestones. - Ensure frequency and schedule match targets set in the ITT and allow sufficient time for data to inform decision-making within the nexus framework. | - List the individuals or positions responsible for data collection and analysis (e.g., community volunteers, field staff, project managers, local partners, external consultants). Use position titles to ensure clarity in case of personnel changes. - Include this information in budgeting and capacity-building plans to ensure adequate resources for M&E activities under the nexus approach. | - Describe the process for compiling and analyzing data. For example, survey data may require statistical analysis, while qualitative data may involve thematic coding or community validation. - Include questions the project team may want to ask to better understand the data (e.g., trends, anomalies, or patterns across humanitarian, development, and peacebuilding outcomes). | - This column identifies the intended audience and use of the information. - Identify the intended audience and purpose of the information. For example: - Humanitarian actors : To monitor immediate needs and response effectiveness. - Development practitioners : To track long-term resilience and systemic change. - Peacebuilding stakeholders : To assess social cohesion, governance improvements, or conflict resolution. - Ensure data is linked to decision-making and accountability within the nexus framework. Eliminate unnecessary indicators or analyses that do not contribute to actionable insights. | - Identify which reports each indicator will appear in (e.g., donor reports, internal monitoring reports, community feedback mechanisms). - Specify how findings will be formatted (e.g., tables, graphs, maps, histograms, narrative reports) to ensure relevance for each stakeholder group. - Use communication and reporting mapping to streamline reporting processes and increase the likelihood of feedback on reported information.

## d. M&E Matrix Example
Project Name: |  |  |  | Project Location: |  |  |  | Project Year:
Identifier |  |  |  | Partner: |  |  |  | Project Start Date:
Project Sector(s): | [7 empty] | Project End Date:
PERFORMANCE INDICATORS |  |  |  | DATA GATHERING |  |  |  | ANALYSIS, USE, REPORTING
Indicator | Indicator Definition | Nexus Domain/Sector | Unit of Measurement | Method | Means of Verification | Frequency and Schedule | Reponsible person/ team | Data Analysis | Information Use/Audience | Reporting
GOAL: Communities in Yemen are more resilient to crises as a result of integrated humanitarian assistance, development cooperation, and peacebuilding efforts.
OUTCOME 1: Households in conflict-affected areas of Yemen have improved livelihoods and economic resilience
Indicator 1.a: % increase in household income from diversified livelihood activities. | % increase calculation: ((new period income value - prior period income value)/prior period income value)) * 100 HH calculation: (income increase of men + income increase of women)/# members in HH with income ITT Calculation: sum of all HH income increase/total # HH Disaggregated by income earned by men and women within the household. | Interlinked Indicators: Each indicator should reflect at least two Nexus sectors | Unit (s): Men and Women (in HH with income) Household | Baseline: 1. Household survey Monitoring: 2. Census Endline: N/A | 1. Consultant database/Baseline Report 2.1. ITT 2.2. Director database 2.3. Consolidated livelihood records 2.4 Community group records | 1. Beginning of project (Mar. 31, 2015) 2.1 Annually (Jan. 30) 2.2 Annually (Jan. 15) 2.3. Annually (Jan. 2) 2.4. Ongoing | 1. Consultant 2.1. Project Manager 2.2. Data entry officer 2.3. Field officer 2.4. Community group record keeper | Are men and women's income rates different? If so, why? How much of the household income is being used for livelihood diversification? What is the minimum income threshold that creates economic resilience? | Project management team to determine if income levels are increasing sufficiently to create economic resilience. Community leaders to identify which households are more successful and how others can improve income generation. | Quarterly ADO progress reports.
OUTPUT 1.1: Target communities have improved access to financial services and resources
Indicator 1.1.a: # of savings and credit groups/cooperatives formed and strengthened. | Calculation: Count number of formal/informal groups involved in savings and credit activities Savings and Credit Group/Cooperative: Mobilizing funds at the community level. Formed: created Strengthened: Trained on purpose, norms, and conflict-sensitive practices |  | Unit: Number of Saving and Credits groups | Ongoing monitoring; Cooperative/self-help group meetings Who responsible for Baseline data | 1. ITT 2. Project Coordinator database 3. Social Mobilizer report | 1. Quarterly 2. Quarterly 3. Monthly | 1. Program Manager 2. Project Coordinator 3. Social Mobilizer | Is the number of groups increasing over time? Are the groups getting stronger and/or improving their ability to provide services? Are the groups contributing to social cohesion and conflict resolution? | Impelementation Partner and local authorities | Monthly/Quarterly donor reports and community feedback sessions.

## e. M&E Matrix (Blank)
M&E Matrix
Project Name: | [8 empty] | Project Location: | [11 empty] | Project Year:
Project Code: | [8 empty] | Project Holder: | [11 empty] | Project Start Date:
Project Sector(s): | [8 empty] | Donor: | [11 empty] | Project End Date:
PERFORMANCE INDICATORS |  |  |  | Targeted BNFs | [16 empty] | DATA GATHERING |  |  |  | ANALYSIS, USE, REPORTING
Indicator | Indicator Definition | Nexus Domain/Sector | Unit of Measurement/ Disaggregatetion | Male |  |  |  |  | Female |  |  |  |  | Total Beneficiaries | Total HHs | IDPs | H.C | Marginalized | PWD | Returnees | Method | Mean of Verification | Frequency and Schedule | Reponsible person/ team | Data Analysis | Information Use/Audience | Reporting Deadline
|  |  |  | < 5 | 5-17 | 18-59 | 60> | Total | < 5 | 5-17 | 18-59 | 60> | Total
GOAL:
OUTCOME 1:
Indicator 1.1:
Indicator 1.2:
OUTPUT 1.1:
Indicator 1.1.1
Indicator 1.1.3
OUTPUT 1.3:
Indicator 1.3.1
Indicator 1.3.2
OUTPUT 1.4:
Indicator 1.4.1
Indicator 1.4.2
Output 1.5
Indicator 1.5.1
Indicator 1.5.2
Output 1.6
Indicator 1.6.1
Indicator 1.6.2

## f. Baseline Table Description
TOOL SUMMARY: BASELINE TABLE
Purpose | The purpose of this tool is to ensure that all relevant, and only relevant, baseline data information is collected and documented. The baseline information is later used to determine targets and track progress across humanitarian assistance, development cooperation, and peacebuilding efforts within the nexus framework. NOTE: The Baseline is NOT a Needs Assessment. The Baseline collects starting data for indicators and normally does not collect information that will require the project theory of change to be adjusted. The Baseline Table should reflect the interconnected nature of humanitarian, development, and peacebuilding objectives, ensuring alignment with the nexus approach.
Information Sources | The project team should have the following information before starting work on the Baseline:
· Complete M&E Matrix (aligned with the nexus approach)
· Project Proposal (Initial M&E Plan) incorporating humanitarian, development, and peacebuilding objectives
· Guidance Documents: - CRS SMILER Guide - IFRC Project Planning Guidance Manual - Relevant nexus-specific frameworks (e.g., UNDP’s Triple Nexus Framework, OECD DAC recommendations)
Who | One person should be chosen to lead the baseline process. This person is responsible for ensuring the table is completed but is not necessarily responsible for collecting all the data. If a consultant is hired to collect primary data, he/she should be responsible for completing the table for the assigned indicators. - Ensure the lead person coordinates closely with humanitarian, development, and peacebuilding teams to align baseline data collection with the nexus approach.
When | According to the policy regarding the submission of Detailed M&E Plans and indicator baseline values of projects starting as of April 1, 2025, the final submission of the Detailed M&E Plan (M&E Matrix, Baseline Table, and the Indicator Tracking Table) must not exceed the following deadlines:
· Projects of less than one year of duration: 60 days from project start date
· Projects between one and three years of duration: 90 days from project start date
· Projects between three and five years of duration: 120 days from project start date
· Nexus-Specific Timing Considerations: Align baseline data collection with seasonal variations, cultural calendars, and conflict dynamics in the target area. For example: - Avoid data collection during peak conflict periods or harvest seasons. - Consider timing around humanitarian crises (e.g., food shortages) or peacebuilding milestones (e.g., ceasefires).
Requirements | REQUIREMENTS:
· Filling out this table is required for all UNRESTRICTED projects.
· For RESTRICTED projects, donor requirements should be followed. If there are no donor requirements, default to these guidelines.
· If a consultant is hired, he/she should provide a database with all the cleaned data from surveys for project records to ensure transparency and validity.
· The information contained in the Baseline Table should only be modified if changes are made to indicators or their definitions that respond to specific and documented technical feedback that complies with donor and organizational standards.
o If changes are made, document and report the reason why the changes were made and how it will impact any other aspects of the project's M&E system and/or project implementation. It is recommended not to eliminate the rows of the indicators that have been changed. Rather, it is suggested to create another row to record the new version of the indicator even if only minor changes have been made to the definition or any other aspect of it. The Comments column can also be used to explain all that is considered worth explaining.
o If changes are made to the Baseline Table, ensure that headquarters, partners, and stakeholders involved in the nexus approach have and use the up-to-date version.
o Staff need to ensure that the most up-to-date document is stored in the organization’s database (e.g., Phoenix).
Tips | · Those who will use the Baseline Table should fill it out. This allows the project team to verify their understanding of the definition and method used to collect the baseline data and apply this same understanding for ongoing data collection or data collection at the end of the project (endline).
· Make sure to define who should take "ownership" of the Baseline Table. This involves: - Ensuring the table is finalized. - Ensuring all interested parties understand the information contained in it and have the final versions. - Incorporating any future changes fully into the project plan and sharing them with all stakeholders. - The same person should also be in charge of the Indicator Tracking Table and the Activity Tracking Table .
· If the baseline is being conducted internally and there are questions about sample size calculations, contact your relevant M&E representative.
· Baseline studies establish the starting point for each indicator, which is necessary for determining if indicator targets defined in the project design need adjustment.
· Nexus-Specific Tips: Ensure baseline data reflects linkages between humanitarian, development, and peacebuilding efforts. For example: - Humanitarian indicators: Immediate needs (e.g., food security, shelter). - Development indicators: Long-term resilience (e.g., livelihoods, education). - Peacebuilding indicators: Social cohesion, governance improvements, or conflict resolution.
How to Address Gender Issues | · Sex-disaggregate data of all indicators for which people are the unit of measure.
· Include both qualitative and quantitative indicators to capture gender dynamics and their intersection with humanitarian, development, and peacebuilding outcomes.
· Ensure gender-sensitive indicators are included to monitor progress toward reducing inequalities and promoting inclusive development and peace.
Key Considerations for the Nexus Approach | · Humanitarian-Development-Peace Linkages: Ensure indicators reflect the interconnections between humanitarian assistance, development cooperation, and peacebuilding efforts. For example: - Humanitarian indicators might focus on immediate needs (e.g., food security, shelter). - Development indicators might track long-term resilience-building (e.g., livelihoods, education). - Peacebuilding indicators might measure social cohesion, conflict resolution, or governance improvements.
· Context Sensitivity: Tailor indicators to the local context, considering the unique challenges and opportunities at the intersection of humanitarian crises, development gaps, and peacebuilding priorities.
· Participatory Approaches: Engage affected communities, local stakeholders, and partners in defining indicators and data collection methods to ensure relevance and ownership.
· Iterative Learning: Treat the Baseline Table as a living document. Regularly review and adapt it to respond to emerging challenges and opportunities within the nexus framework.

## g. Baseline Table Cheat Sheet
Indicator table for the Baseline of "Name of the Project"
Name of the project: |  |  |  | Location of the project: |  |  | Project duration (in years):
Identifier: |  |  |  | Partner: |  |  | Project start date:
Sector(s) of the project: | [6 empty] | Project end date:
INDICATORS |  |  |  | TARGETS AND BASELINE VALUES |  |  | DOCUMENTATION
Indicator | Indicator definition | Nexus Domain/Sector | Unit of measurement | Life of project target | Baseline value | Date of the baseline value | Source of the baseline value | Comments
- Indicators are taken directly from the M&E Matrix. Include all indicators, ensuring they align with the nexus approach (bridging humanitarian assistance, development cooperation, and peacebuilding efforts). - For indicators with a starting value of zero, provide a clear explanation of why this value is zero and how it relates to the project’s goals within the nexus framework. Key Considerations for the Nexus Approach: - Humanitarian-Development-Peace Linkages: Ensure indicators reflect the interconnections between humanitarian assistance, development cooperation, and peacebuilding efforts. For example: Humanitarian indicators: Immediate needs (e.g., food security, shelter). Development indicators: Long-term resilience (e.g., livelihoods, education). Peacebuilding indicators: Social cohesion, governance improvements, or conflict resolution. Context Sensitivity: Tailor indicators and methods to the local context, considering unique challenges and opportunities at the intersection of crises, development gaps, and peacebuilding priorities. Participatory Approaches: Engage affected communities, local stakeholders, and partners in defining indicators and collecting baseline data to ensure relevance and ownership. | - Indicator definitions come directly from the M&E Matrix. They are repeated here for ease of reading and understanding in relation to baseline values. - Ensure definitions reflect linkages between humanitarian, development, and peacebuilding outcomes. Refer to the revised M&E Matrix Cheat Sheet for more information on indicator definitions. | Interlinked Indicators: Each indicator should reflect at least two Nexus sectors | - A unit of measure is a standard quantity that establishes the magnitude of the indicator’s value. It answers the question: What are we counting? Common units include: - Simple: People, kilos, tons, plots, hectares, etc. - Complex: Productivity (e.g., kilos per hectare), density (e.g., trees per plot), poverty (e.g., income per year or per hectare). - Ensure units are appropriate for the context and aligned with the nexus approach (e.g., resilience scores, conflict resolution rates, food security levels). | - This is the value of the indicator that the project team hopes to achieve by the end of the project. It is expressed in the unit of measurement defined in the previous column. - Examples: 300 people trained in soil management practices, 100 coffee plantations managed with best pruning E7, cacao productivity of 2 tons per hectare, net income of $150 per family from legume sales. - For quantitative indicators based on mathematical formulas (e.g., percentages, rates), redocument the components of the formula (numerator and denominator). - Gender and Inclusion: Disaggregate data by sex, age, and other relevant variables to address inequalities and promote inclusive development and peace. Include gender-sensitive indicators to monitor progress toward reducing disparities and empowering women and marginalized groups. | - This is the value of the indicator at the beginning of the project, expressed in the same unit of measure as the target. -Output Indicators: Often start at zero, as these measure the results of implementing project activities. However, depending on the logframe, some outcome-level indicators (e.g., production and productivity) may be assigned to the output level. - Examples: Number of people trained, number of infrastructures built, number of pieces of equipment delivered, number of plans developed and approved, number of contracts signed with buyers. - Outcome Indicators: Measure conditions already present in the target population and show changes in behavior, attitudes, or practices. - Examples: Number of producers applying best practices, number of students washing hands according to key steps, annual net family income from coffee sales. | - The date (month and year) when the initial value was gathered in the field from a primary source (e.g., producer survey, cooperative registry). - If the value is obtained from a secondary source (e.g., needs assessment, agrarian census, studies by other organizations), document the publication date of the source. - Align timing with seasonal variations, cultural calendars, and conflict dynamics in the target area (e.g., avoid data collection during peak conflict periods or harvest seasons). | - Refers to the document (physical or electronic) in which the indicator value is stated. These can be primary or secondary sources. - Primary Sources: Data collected directly by the organization or its partners (e.g., household surveys, registries, databases, reports). Specify the type of document (e.g., cooperative registry of cacao sales). - Secondary Sources: Data collected by others (e.g., agrarian census, UN reports, studies by peer organizations). Clearly state the title of the document, author(s), and publication date. - If the value comes from a website (e.g., Ministry of Agriculture, National Statistics Department), document the URL and save a copy of the screen (using print screen) showing the date the data was collected. | - Use this space to document additional information about the indicator that the project team deems valuable for better understanding project results. - Examples of complementary information: - For production or productivity indicators, explain if the original unit of measure was locally used (e.g., manzanas in Nicaragua) and converted to hectares due to donor requirements. Provide equivalences (e.g., 1 mz = 0.7 hectares). - If the indicator value corresponds to specific geographic areas participating in the project (and not others), explain this here. - If the indicator value was obtained using a sample (e.g., probabilistic, by quotas, voluntary) or a census, specify the sampling method. - Document any adjustments made to align indicators with the nexus approach (e.g., integrating humanitarian, development, and peacebuilding dimensions).

## h. Baseline Table (Blank)
Indicator table for the Baseline of "Name of the Project"
Name of the project: |  |  |  | Location of the project: |  |  | Project duration (in years):
Identifier: |  |  |  | Partner: |  |  | Project start date:
Sector(s) of the project: | [6 empty] | Project end date:
INDICATORS |  |  |  | TARGETS AND BASELINE VALUES |  |  | DOCUMENTATION
Indicator | Indicator definition | Nexus Domain/Sector | Unit of measurement | Life of project target | Baseline value | Date of the baseline value | Source of the baseline value | Comments
GOAL:
OUTCOME 1:
OUTPUT 1.1:
Activity 1.1.1
Activity 1.1.2
Activity 1.1.3
OUTPUT 1.3:
Activity 1.3.1
Activity 1.3.2
Activity 1.3.3
OUTPUT 1.4:
Activity 1.4.1
Activity 1.4.2
Activity 1.4.3
Output 1.5
Activity 1.5.1
Activity 1.5.2
Activity 1.5.3
Output 1.6
Activity 1.6.1
Activity 1.6.2
Activity 1.6.3

## i. ITT Description
TOOL SUMMARY: INDICATOR TRACKING TABLE INSTRUCTIONS
Purpose | The Indicator Tracking Table (ITT) is a tool used as a tracking mechanism for all project indicators, ensuring alignment with the nexus approach —a strategic framework that bridges humanitarian assistance, development cooperation, and peacebuilding efforts. - The ITT helps monitor progress across the humanitarian-development-peace nexus, ensuring that projects effectively address immediate needs, long-term resilience, and social cohesion. - It serves as a critical management tool for timely adjustments and improvements to project implementation, fostering sustainable and resilient outcomes.
Information Sources | The project design team should have the following information before starting the ITT:
· Needs Assessment: Reflecting humanitarian, development, and peacebuilding priorities.
· Logframe: Aligned with the nexus approach, bridging immediate needs, systemic change, and conflict resolution.
· Project Proposal: Incorporating objectives and indicators from all three pillars of the nexus framework.
· Baseline Data: Collected in alignment with the nexus approach, reflecting starting points for humanitarian, development, and peacebuilding indicators.
· M&E Matrix: Ensuring SMART indicators and data collection methods tailored to the nexus framework.
Who | - The ITT should be completed by the partner, reviewed by the ADO Project Manager (PM), and included in each Project Progress Report . - Ensure collaboration between humanitarian, development, and peacebuilding teams to align data collection and reporting with the nexus approach.
When | The ITT is a sub-tool of the Detailed M&E Plan and should therefore be completed according to the timeframe set out for the completion of the Detailed M&E Plan. - Projects of less than one year : Within 60 days of project start date. - Projects between one and three years : Within 90 days of project start date. - Projects between three and five years : Within 120 days of project start date. It is normally developed after the M&E Matrix has been completed and after baseline data has been collected.
Requirements | MANDATORY REQUIREMENTS:
· Every project is required to have an ITT.
· The ITT requires that the project sets targets for indicators on quarterly, annual, and life of project timeframes.
· The ITT should be updated with actual data for every reporting period. The ITT should be updated before beginning the narrative Project Progress Report.
NEXUS-SPECIFIC GUIDANCE:
Targets should reflect linkages between humanitarian, development, and peacebuilding efforts. For example: - Humanitarian targets: Immediate needs (e.g., food security, shelter). - Development targets: Long-term resilience (e.g., livelihoods, education). - Peacebuilding targets: Social cohesion, governance improvements, or conflict resolution.
REPORTING FREQUENCY:
· The ITT is most effective when used on a quarterly basis , providing project managers with regular data to make timely adjustments and improvements. · If the required reporting period is semiannually, complete the ITT quarterly but focus the analysis in the Project Progress Report on progress for the entire six-month period.
TARGET REVISIONS:
Targets can be revised, but there should be clear and convincing reasoning behind the revision. Indicator target revisions are not common and should only occur when there has been a major change to the scope or context of the project. For restricted projects , consult with the ADO Grants Manager before revising indicator targets. Communicate target revisions clearly to the donor. For unrestricted projects , coordinate with the Program Associate before revising indicator targets. If approval is given to revise indicator targets: Highlight revised targets in progress reports and provide clear and specific reasoning for the revisions. Ensure that new targets are updated in the ITT and that all subsequent quarterly, annual, and life-of-project targets reflect the revision.
RECOMMENDATIONS:
· The “Status” column in the ITT can indicate: - The date the indicator data is expected to start and end. - If data will only be collected at baseline and endline. - If the indicator is completed or ongoing. · The “Status” column is NOT to be used to provide any narrative explanation about the indicator. Narrative explanations should be included in the Project Progress Report .
Tips | Learning from Missed Targets: Not meeting a target should be viewed as a learning experience, not as a failure. · Discuss why actual data is over or under a target to understand what adjustments to the project’s implementation should be made. · Set ambitious but realistic targets by linking them closely to the project’s detailed implementation plan and the nexus approach.
Use the ITT as a Key Analysis Tool: · Analyze why or why not targets were met to help you understand what adjustments to the project’s implementation should be made. · Use findings to inform decisions about humanitarian assistance, development cooperation, and peacebuilding activities.
Share Key Findings: · Key findings from the ITT analysis become central information for project reports and can be shared with all relevant stakeholders, including humanitarian actors, development practitioners, and peacebuilding experts.
Key Considerations for the Nexus Approach | Humanitarian-Development-Peace Linkages: · Ensure indicators reflect the interconnections between humanitarian assistance, development cooperation, and peacebuilding efforts. For example: - Humanitarian indicators: Immediate needs (e.g., food security, shelter). - Development indicators: Long-term resilience (e.g., livelihoods, education). - Peacebuilding indicators: Social cohesion, governance improvements, or conflict resolution.
Context Sensitivity: · Tailor indicators and targets to the local context, considering unique challenges and opportunities at the intersection of crises, development gaps, and peacebuilding priorities.
Participatory Approaches: · Engage affected communities, local stakeholders, and partners in defining targets and analyzing progress to ensure relevance and ownership.
Gender and Inclusion: · Disaggregate data by sex, age, and other relevant variables to address inequalities and promote inclusive development and peace. · Include gender-sensitive indicators to monitor progress toward reducing disparities and empowering women and marginalized groups.
Iterative Learning: · Treat the ITT as a living document. Regularly review and adapt it to respond to emerging challenges and opportunities within the nexus framework.

## j. ITT "Project Name" Year 1
INDICATOR TRACKING TABLE
Project Name: | [33 empty] | Project Beneficiaries | Male |  |  |  |  | Female |  |  |  |  | Total HHs | IDPs | H.C | Marginalized | PWD | Returnees | Others | % of Achived
Report Period: | [11 empty] | Partner: | [12 empty] | Project Year | [9 empty] | < 5 | 5-17 | 18-59 | 60> | Total | < 5 | 5-17 | 18-59 | 60> | Total
Identifier: | [11 empty] | Project Location: | [12 empty] | Project Start Date: | [8 empty] | Direct
Project Sector(s): | [24 empty] | Project End Date: | [8 empty] | Indirect
[34 empty] | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RESULTS |  |  | Project Baseline |  |  | Q1 Reporting Period Date X - Date Y | [13 empty] | Q2 Reporting Period Date X - Date Y | [13 empty] | Q3 Reporting Period Date X - Date Y | [13 empty] | Q4 Reporting Period Date X - Date Y | [13 empty] | Annual Target | Per Year | [12 empty] | Life of Project Target | Life of Project Actual | [12 empty] | Project Component | Status
[6 empty] | Target | Actual | [12 empty] | Target | Actual | [12 empty] | Target | Actual | [12 empty] | Target | Actual | [13 empty] | Actual | [13 empty] | Actual
|  |  | Location | Total Target | Unit |  | < 5 | 5-17 | 18-59 | 60> | Total | Total HHs | IDPs | H.C | Marginalized | PWD | Returnees | Others | % of Achived |  | < 5 | 5-17 | 18-59 | 60> | Total | Total HHs | IDPs | H.C | Marginalized | PWD | Returnees | Others | % of Achived |  | < 5 | 5-17 | 18-59 | 60> | Total | Total HHs | IDPs | H.C | Marginalized | PWD | Returnees | Others | % of Achived |  | < 5 | 5-17 | 18-59 | 60> | Total | Total HHs | IDPs | H.C | Marginalized | PWD | Returnees | Others | % of Achived |  | < 5 | 5-17 | 18-59 | 60> | Total | Total HHs | IDPs | H.C | Marginalized | PWD | Returnees | Others | % of Achived |  | < 5 | 5-17 | 18-59 | 60> | Total | Total HHs | IDPs | H.C | Marginalized | PWD | Returnees | Others | % of Achived
GOAL: |  | Nexus Domain/Sector
OUTCOME 1:
Indicator 1.1: | [18 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Males | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Females | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
Indicator 1.2: | [18 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Males | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Females | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
OUTPUT 1.1:
Indicator 1.1.1 | [18 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Males | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Females | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
#REF! | [18 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Males | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Females | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
OUTPUT 1.3:
Indicator 1.3.1 | [18 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Males | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Females | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
Indicator 1.3.2 | [18 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Males | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Females | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
#REF!
#REF! | [18 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Males | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Females | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
#REF! | [18 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Males | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Females | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
OUTPUT 1.4:
Indicator 1.4.1 | [18 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Males | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Females | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
#REF! | [18 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Males | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Females | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
Output 1.5
Indicator 2.2.a: | [18 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Males | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Females | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
#REF! | [18 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Males | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Females | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
#REF!
Indicator 1.6.1 | [18 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Males | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Females | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
Indicator 1.6.2 | [18 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Males | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Females | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
#REF!
#REF! | [18 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Males | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Females | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
#REF! | [18 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Males | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Females | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
#REF!
#REF! | [18 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Males | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Females | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
#REF! | [18 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Males | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Females | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
#REF!
#REF! | [18 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Males | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Females | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
#REF! | [18 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Males | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Females | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
#REF!
#REF! | [18 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Males | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Females | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
#REF! | [18 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Males | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Females | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
#REF!
#REF! | [18 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Males | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Females | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
#REF! | [18 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Males | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Females | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
Note on CO7: The “Status” column in the ITT can indicate the date the indicator data is expected to start and end, if it will only be collected at baseline and endline, if it is completed, or if it is ongoing. The “Status” column is NOT to be used to provide any narrative explanation about the indicator. This should be done in the Project Progress Report.

## k. ATT Description
TOOL SUMMARY: ACTIVITY TRACKING TABLE INSTRUCTIONS
Purpose | The Activity Tracking Table (ATT) is a complementary tool to the Indicator Tracking Table (ITT) and serves as a key mechanism for tracking project activities in alignment with the nexus approach —a strategic framework that bridges humanitarian assistance, development cooperation, and peacebuilding efforts.
· The ATT allows activities to be tracked in a summary manner, ensuring clarity without complicating the ITT. · It assists the project team, ADO Project Manager (PM), and ADO HQ in monitoring progress toward achieving project outputs while fostering linkages between humanitarian, development, and peacebuilding objectives. · By elaborating on the general Project Work Plan , the ATT lists all project activities and their estimated targets for each reporting period, ensuring alignment with the nexus framework.
Information Sources | The project team should have the following information before starting the ATT:
· Logframe: Aligned with the nexus approach, bridging immediate needs, systemic change, and conflict resolution.
· Project Proposal: Incorporating objectives and activities from all three pillars of the nexus framework.
· M&E Matrix: Ensuring SMART indicators and data collection methods tailored to the nexus approach.
· Indicator Tracking Table: Linking activity completion to indicator progress across humanitarian, development, and peacebuilding efforts.
Who | ·The ATT should be completed and updated by the partner, reviewed by the ADO PM, and included in each Project Progress Report . · Ensure collaboration between humanitarian, development, and peacebuilding teams to align activity tracking with the nexus approach.
When | The ATT is a sub-tool of the Detailed M&E Plan and should therefore be completed according to the timeframe set out for the completion of the Detailed M&E Plan: - Projects of less than one year : Within 60 days of project start date. - Projects between one and three years : Within 90 days of project start date. - Projects between three and five years : Within 120 days of project start date.
Requirements | MANDATORY REQUIREMENTS:
· Every project is required to have an ATT.
· The ATT requires setting targets for activity completion on quarterly , annual , and life of project timeframes.
· The ATT should be updated with actual data for every reporting period. Update the ATT before beginning the narrative Project Progress Report.
NEXUS-SPECIFIC GUIDANCE:
Targets should reflect linkages between humanitarian, development, and peacebuilding efforts. For example: - Humanitarian targets: Immediate needs (e.g., food security, shelter). - Development targets: Long-term resilience (e.g., livelihoods, education). - Peacebuilding targets: Social cohesion, governance improvements, or conflict resolution.
REPORTING FREQUENCY:
· The ATT is most effective when used on a quarterly basis , providing project managers with regular data to make timely adjustments and improvements. · If the required reporting period is semiannually, complete the ATT quarterly but focus the analysis in the Project Progress Report on progress for the entire six-month period.
LINKAGE TO RESULTS:
· While the completion of activities tells us little about changes in development conditions or people’s lives, it is the results of these activities that are significant. · Use the ATT to track activity completion as a critical management tool, ensuring activities contribute to achieving impact-level outcomes across the nexus framework.
SECTION 3.1.A OF PROJECT PROGRESS REPORT:
· Section 3.1.a. of the Project Progress Report is dedicated to analyzing progress toward meeting activity targets. This allows the project team to explain in detail the simplified quantitative activity tracking of the ATT.
Tips | Learning from Missed Targets: Not meeting a target should be viewed as a learning experience, not as a failure. · Discuss why actual data is over or under a target to understand what adjustments to the project’s implementation should be made. · Set ambitious but realistic targets by linking them closely to the project’s detailed implementation plan and the nexus approach.
Use the ATT as a Key Analysis Tool: · Analyze why or why not targets were met to help you understand what adjustments to the project’s implementation should be made. · Use findings to inform decisions about humanitarian assistance, development cooperation, and peacebuilding activities.
Keep It Simple and Clear: · Reporting detailed information about sub-tasks to complete activities can be time-consuming and confusing for report reviewers at the regional and Headquarters level. Keep the ATT simple, clear, and concise.
Key Findings for Stakeholders: · Key findings from the ATT analysis become central information for project reports and can be shared with all relevant stakeholders, including humanitarian actors, development practitioners, and peacebuilding experts.
Key Considerations for the Nexus Approach | Humanitarian-Development-Peace Linkages: · Ensure indicators reflect the interconnections between humanitarian assistance, development cooperation, and peacebuilding efforts. For example: - Humanitarian indicators: Immediate needs (e.g., food security, shelter). - Development indicators: Long-term resilience (e.g., livelihoods, education). - Peacebuilding indicators: Social cohesion, governance improvements, or conflict resolution.
Context Sensitivity: · Tailor indicators and targets to the local context, considering unique challenges and opportunities at the intersection of crises, development gaps, and peacebuilding priorities.
Participatory Approaches: · Engage affected communities, local stakeholders, and partners in defining targets and analyzing progress to ensure relevance and ownership.
Gender and Inclusion: · Disaggregate data by sex, age, and other relevant variables to address inequalities and promote inclusive development and peace. · Include gender-sensitive indicators to monitor progress toward reducing disparities and empowering women and marginalized groups.
Iterative Learning: · Treat the ATT as a living document. Regularly review and adapt it to respond to emerging challenges and opportunities within the nexus framework.

## l. ATT "Project Name" Year 1
INDICATOR TRACKING TABLE
Project Name: | [33 empty] | Project Beneficiaries | Male |  |  |  |  | Female |  |  |  |  | Total HHs | IDPs | H.C | Marginalized | PWD | Returnees | Others | % of Achived
Report Period: | [11 empty] | Partner: | [12 empty] | Project Year | [9 empty] | < 5 | 5-17 | 18-59 | 60> | Total | < 5 | 5-17 | 18-59 | 60> | Total
Identifier: | [11 empty] | Project Location: | [12 empty] | Project Start Date: | [8 empty] | Direct
Project Sector(s): | [24 empty] | Project End Date: | [8 empty] | Indirect
[34 empty] | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RESULTS |  |  | Project Baseline |  |  | Q1 Reporting Period Date X - Date Y | [13 empty] | Q2 Reporting Period Date X - Date Y | [13 empty] | Q3 Reporting Period Date X - Date Y | [13 empty] | Q4 Reporting Period Date X - Date Y | [13 empty] | Annual Target | Per Year | [12 empty] | Life of Project Target | Life of Project Actual | [12 empty] | Project Component | Status
[6 empty] | Target | Actual | [12 empty] | Target | Actual | [12 empty] | Target | Actual | [12 empty] | Target | Actual | [13 empty] | Actual | [13 empty] | Actual
|  | Nexus Domain/Sector | Location | Total Target | Unit |  | < 5 | 5-17 | 18-59 | 60> | Total | Total HHs | IDPs | H.C | Marginalized | PWD | Returnees | Others | % of Achived |  | < 5 | 5-17 | 18-59 | 60> | Total | Total HHs | IDPs | H.C | Marginalized | PWD | Returnees | Others | % of Achived |  | < 5 | 5-17 | 18-59 | 60> | Total | Total HHs | IDPs | H.C | Marginalized | PWD | Returnees | Others | % of Achived |  | < 5 | 5-17 | 18-59 | 60> | Total | Total HHs | IDPs | H.C | Marginalized | PWD | Returnees | Others | % of Achived |  | < 5 | 5-17 | 18-59 | 60> | Total | Total HHs | IDPs | H.C | Marginalized | PWD | Returnees | Others | % of Achived |  | < 5 | 5-17 | 18-59 | 60> | Total | Total HHs | IDPs | H.C | Marginalized | PWD | Returnees | Others | % of Achived
OUTPUT 1.1:
ACTIVITY 1.1. A: | [18 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Males | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Females | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
ACTIVITY 1.1. B: | [18 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Males | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Females | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
OUTPUT 1.2:
ACTIVITY 1.2. A: | [18 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Males | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Females | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
ACTIVITY 1.2. B: | [18 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Males | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Females | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
OUTPUT 1.3:
ACTIVITY 1.3. A: | [18 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Males | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Females | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
ACTIVITY 1.3. B: | [18 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Males | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Females | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
OUTPUT 1.4:
ACTIVITY 1.4. A: | [18 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Males | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Females | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
ACTIVITY 1.4. B: | [18 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Males | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Females | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
OUTPUT 1.5:
ACTIVITY 1.5. A: | [18 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Males | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Females | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
ACTIVITY 1.5. B: | [18 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Males | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Females | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
OUTPUT 1.#:
ACTIVITY 1.#. A: | [18 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Males | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Females | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
ACTIVITY 1.#. B: | [18 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Males | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
| Females | [17 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA | [13 empty] | NA
Note on CO7: The “Status” column in the ITT can indicate the date the indicator data is expected to start and end, if it will only be collected at baseline and endline, if it is completed, or if it is ongoing. The “Status” column is NOT to be used to provide any narrative explanation about the indicator. This should be done in the Project Progress Report.

## m. Project Wrok Description
TOOL SUMMARY: Project Work Plan Instructions
Purpose | The Project Work Plan is a critical tool for planning, organizing, and tracking project activities to achieve desired outcomes. When aligned with the nexus approach , it ensures that humanitarian assistance, development cooperation, and peacebuilding efforts are strategically integrated to address immediate needs, build long-term resilience, and foster social cohesion.
· The Work Plan serves as a roadmap for implementing activities in a way that bridges gaps between these three pillars, ensuring coherence and synergy across interventions. · It also supports iterative learning and adaptation, enabling projects to respond effectively to evolving contexts and challenges.
Information Sources | Before developing the Project Work Plan, the project team should gather and review the following information:
· Logframe: Ensure the Logframe reflects the nexus approach by linking outputs, outcomes, and goals across humanitarian, development, and peacebuilding objectives.
· Project Proposal: Incorporate activities and timelines from the proposal, ensuring alignment with the nexus framework.
· M&E Matrix: Use SMART indicators and data collection methods tailored to the nexus approach to guide activity planning.
· Baseline Data: Reflect starting points for activities and ensure they align with humanitarian, development, and peacebuilding priorities.
· Stakeholder Input: Engage affected communities, local stakeholders, and partners to ensure activities are context-sensitive and inclusive.
Who | ·The Project Work Plan should be developed collaboratively by the project team, including representatives from humanitarian, development, and peacebuilding sectors. · The plan should be reviewed by the ADO Project Manager (PM) and shared with all relevant stakeholders, including donors, partners, and community members.
When | ·The Project Work Plan should be finalized during the project design phase, after completing the Logframe, M&E Matrix, and Baseline Table. · It should be updated regularly throughout the project lifecycle to reflect changes in context, emerging challenges, or new opportunities within the nexus framework.
Requirements | MANDATORY REQUIREMENTS:
1. Activity Alignment with the Nexus Approach:
Ensure all activities are explicitly linked to one or more pillars of the nexus framework: - Humanitarian targets: Immediate needs (e.g., food security, shelter). - Development targets: Long-term resilience (e.g., livelihoods, education). - Peacebuilding targets: Social cohesion, governance improvements, or conflict resolution. Activities should demonstrate clear linkages between these pillars to ensure coherence and synergy.
2. Timeline and Milestones:
· Set realistic timelines for each activity, considering seasonal variations, cultural calendars, and conflict dynamics in the target area. · Define key milestones for monitoring progress and making timely adjustments.
3. Resource Allocation:
· Allocate resources (financial, human, material) to each activity, ensuring equitable distribution across humanitarian, development, and peacebuilding efforts. · Include contingency plans for resource reallocation in response to changing needs or emergencies.
4. Responsibility Assignment:
· Clearly assign responsibility for each activity to specific individuals or teams, using position titles to ensure clarity in case of personnel changes. · Ensure collaboration between humanitarian, development, and peacebuilding actors to foster joint ownership and accountability.
5. Monitoring and Reporting:
· Link activities to the Indicator Tracking Table (ITT) and Activity Tracking Table (ATT) to ensure alignment with M&E requirements. · Update the Work Plan quarterly to reflect actual progress and adjust targets as needed.
Tips | Collaborative Development: · Involve all stakeholders, including affected communities, in developing the Work Plan to ensure relevance, feasibility, and ownership.
Context Sensitivity: · Tailor activities to the local context, considering unique challenges and opportunities at the intersection of crises, development gaps, and peacebuilding priorities.
Gender and Inclusion: · Disaggregate activity data by sex, age, and other relevant variables to address inequalities and promote inclusive development and peace. · Include gender-sensitive activities to monitor progress toward reducing disparities and empowering women and marginalized groups.
Iterative Learning: · Treat the Work Plan as a living document. Regularly review and adapt it to respond to emerging challenges and opportunities within the nexus framework.
Clear Communication: · Use simple, clear, and concise language to describe activities, timelines, and responsibilities. Avoid overly technical jargon to ensure accessibility for all stakeholders.
Risk Management: · Identify potential risks to activity implementation (e.g., security concerns, resource shortages) and include mitigation strategies in the Work Plan.
Integration of Feedback: · Incorporate feedback from stakeholders, including beneficiaries, into the Work Plan to ensure continuous improvement and alignment with evolving needs
Key Considerations for the Nexus Approach | Humanitarian-Development-Peace Linkages: · Ensure activities reflect the interconnections between humanitarian assistance, development cooperation, and peacebuilding efforts. For example: - Humanitarian activities: Immediate needs (e.g., food security, shelter). - Development activities: Long-term resilience (e.g., livelihoods, education). - Peacebuilding activities: Social cohesion, governance improvements, or conflict resolution.
Sequencing and Coordination: · Sequence activities to ensure smooth transitions between humanitarian, development, and peacebuilding phases. For example, emergency food distribution can transition into livelihood training programs.
Participatory Approaches: · Engage affected communities, local stakeholders, and partners in defining activities and analyzing progress to ensure relevance and ownership.
Conflict Sensitivity: · Design activities to minimize harm and maximize positive impacts on conflict dynamics. For example, prioritize inclusive dialogue forums to prevent tensions.
Sustainability: · Ensure activities contribute to sustainable outcomes by building local capacity and fostering ownership among beneficiaries and stakeholders.

## n. Project WrokPlan
Project WrokPlan
Project Name: | [8 empty] | Project Location: | [7 empty] | Project Year: |  |  |  |  | Project Location: | [10 empty] | Project Year:
Project Code: | [8 empty] | Project Holder: | [7 empty] | Project Start Date: |  |  |  |  | Project Holder: | [10 empty] | Project Start Date:
Project Sector(s): | [8 empty] | Donor: | [7 empty] | Project End Date: |  |  |  |  | Donor: | [10 empty] | Project End Date:
Activities as per Logical Framework |  |  |  | Targeted BNFs | [17 empty] | MoV | Responsible Person/Team | Resources Required | Status (Not Started/In Progress/Completed) | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  | Aug |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec
Code | Activities | Sub-Activites | Nexus Domain/Sector | Male |  |  |  |  | Female |  |  |  |  | Total Beneficiaries | Total HHs | IDPs | H.C | Marginalized | PWD | Returnees | Others |  |  |  |  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
|  |  |  | < 5 | 5-17 | 18-59 | 60> | Total | < 5 | 5-17 | 18-59 | 60> | Total
GOAL:
OUTCOME 1:
OUTPUT 1.1:
Activity 1.1.1
Activity 1.1.2
Activity 1.1.3
OUTPUT 1.3:
Activity 1.3.1
Activity 1.3.2
Activity 1.3.3
OUTPUT 1.4:
Activity 1.4.1
Activity 1.4.2
Activity 1.4.3
Output 1.5
Activity 1.5.1
Activity 1.5.2
Activity 1.5.3
Output 1.6
Activity 1.6.1
Activity 1.6.2
Activity 1.6.3
2. Resource Allocation
Resource Type | Description | Quantity |  | Cost (USD) | Source | Allocated to Activity
3. Risk Management Plan
Risk | Likelihood | Impact |  | Mitigation Strategy | Contingency Plan
5. Monitoring and Reporting Framework
Indicator | Target | Baseline Value |  | Data Collection Method | Frequency of Reporting | Responsible Person/Team | Linked Activity